## Dashboard
City Sheet Table Summaries
- The Forward Sumner/MPO "Project Delivery Task Force FY 2020-23 TIP Project Tracker (Degrees of Concern)" table shows the projects that the MPO Project Delivery Task Force is looking at relative to your city. This comprehensive resource presents information on each project, including the lead agency, project name, degree of concern, improvement type, total cost, and current phase of development.
- The "Local Projects" table presents an overview of various infrastructure projects in your city, focusing on key aspects such as project name, TIP ID#, improvement type, location, lead agency, and total cost. Notably, the TIP ID# column features direct hyperlinks to a dynamic project database, updated and managed by the MPO/Transportation Policy board, providing you with real-time, in-depth information on each project.
- The "2045_RTP_Projects_Submitted" table provides an overview of various projects submitted for consideration in the regional transportation planning process. Each project includes essential details such as the project ID, name, improvement type, applicant, county, RTP ID, TIP#, estimated cost, desired horizon year, and priority. The table also evaluates each project's performance in the following categories: State of Good Repair (20 Max), Safety (30 Max), Congestion (15 Max), Economic Development (15 Max), Environment (10 Max), Alignment with Goals and Objectives (10 Max), and Total Score (100 Max). Projects are ranked and assigned to tiers based on their overall scores, allowing stakeholders to easily understand the priority and impact of each proposal in order to make informed decisions about investments in regional transportation infrastructure.
- The "2045_RTP_Project_Ranking" table presents a comprehensive list of proposed projects, ranked by their priority and impact. Each entry includes important information such as the project ID, applicant, county, proposal, project name, score, rank, tier, and estimated cost. The table also highlights each project's performance in categories like State of Good Repair (SOGR), Safety (SFTY), Congestion (CONG), Economic Development (ECON), Environment (ENVT), Alignment with Goals and Objectives (ALGN), and Transportation Improvement Program ID (TIP ID). This ranking system allows stakeholders to easily identify projects of higher priority and evaluate their potential benefits, aiding in the decision-making process for infrastructure investments in the region.
Grants&FundingCodeDescriptions
- The "Grants&FundingCodeDescriptions" sheet provides a comprehensive list of funding sources for various transportation projects. Each funding source is described along with information on source, administration, allocation, and program details. Notably, the 'Program Details' column contains hyperlinks to direct Federal Transit Authority (FTA) documentation for further information on each program.
- Some of the funding sources include Advanced Transportation and Congestion Management Technologies Deployment (ATCMTD), Congestion Mitigation and Air Quality Program (CMAQ), Emergency Relief Program (ER), Large Urban Transit Formula Funds for Nashville-Davidson Urbanized Area (FTA 5307), and Enhanced Mobility for Seniors and Individuals with Disabilities (FTA 5310). These funding sources come from different levels of government, including federal, state, and local, and are administered by various agencies such as the Federal Highway Administration (FHWA), Federal Transit Administration (FTA), and Tennessee Department of Transportation (TDOT).
PhasesOfWork
- The "PhasesOfWork" sheet presents a list of different phases involved in transportation projects. Each phase has a corresponding code and description, which are as follows:
1. PLAN - Planning: This phase involves the initial assessment and development of project ideas, including feasibility studies, and the identification of project goals and objectives.
2. PE-N - Environmental Review: This phase involves the evaluation of a project's potential environmental impacts, as well as the development of strategies to mitigate any adverse effects.
3. PE-D - Final Design: This phase involves the detailed design and engineering of a project, including the preparation of construction plans and specifications.
4. ROW - Right-of-Way Acquisition: This phase involves acquiring the necessary land or property rights to build the project, which may include negotiations with property owners and the completion of legal processes.
5. UTIL - Utilities Relocation: This phase involves the relocation or adjustment of existing utility infrastructure, such as water, sewer, and electrical systems, to accommodate the project.
6. CONS - Construction: This phase involves the actual building of the project, including site preparation, materials procurement, and the management of construction activities.
7. IMPL - Implementation: This phase involves the final steps to make the project operational, such as system integration, testing, and commissioning.
8. MAIN - Maintenance: This phase involves the ongoing upkeep and repair of the project, ensuring that it remains functional and safe throughout its lifespan.
Sponsor&Organizations
- The "Sponsor&Organizations" sheet provides a list of organizations involved in transportation projects, along with their respective organization types, primary contacts, and associated TIP projects. Each organization has several associated TIP projects, which can be found in the "Associated TIP Projects" column within the sheet. The table includes the following organizations and primary contact information:
Gallatin
Organization Type: Municipal Government
Primary Contact: Bill McCord (william.mccord@gallatin-tn.gov, (615) 452-5400)
Goodlettsville
Organization Type: Municipal Government
Primary Contact: Addam McCormick (amccormick@goodlettsville.gov, (615) 851-2200)
Hendersonville
Organization Type: Municipal Government
Primary Contact: Sarah Lock (slock@hvilletn.org, (615) 822-1016)
Portland
Organization Type: Municipal Government
Primary Contact: Carlton Cobb (ccobb@cityofportlandtn.gov)
Sumner County
Organization Type: County Government
Primary Contact: Josh Suddath (jsuddath@sumnercountytn.gov)
TDOT
Organization Type: State Government
Primary Contact: Jonathan Russell (jonathan.russell@tn.gov)
White House
Organization Type: Municipal Government
Primary Contact: Ceagus Clark (cclark@whitehousetn.gov)
TDOT Table
- The TDOT table displays the Sumner County impacted projects, including regionally significant projects such as NETcorridor (SR 386 - Vietnam Veterans) Phase 1 & 2, and the Portland Bypass. The listed projects involve a range of improvements such as roadway widening, multi-modal transportation, road upgrades, interchange development, and new roadway construction.
Databases&Documentation
- This table contains an overview of various databases and tools related to transportation projects in the Greater Nashville area and Tennessee. It includes information on project status, county, improvement type, and funding sources, as well as online tools for tracking project progress and visual dashboards for easy interpretation. These were the primary sources used during this project.
Welcome to FSEP's Community Development & Infrastructure - Transportation Workbook! An outline of the workbook's contents can be found below and please use the icons in the leftside panel to help navigate through the data.
TDOT 3yr TIP for Fiscal Years '23-'26
- Sumner County impacted projects from the Govenor's annual release of the TDOT 3yr TIP. This information shows the fiscal year '24-'26, and the fiscal year '23-'25 TIP. Hyperlinks are also provided that route directly to the official press releases.

## Gallatin
Project Delivery Task Force FY 2020-23 TIP Project Tracker (Degrees of Concern)
Lead Agency | Project Name | County | Degrees of Concern | Years Programmed | Development Duration | Inactivity Duration | Improvement Type | MPO TIP # | TDOT PIN # | PINI # | Year Entered TIP | Estimated Total Cost | Programmed Construction Year | Active/Current Phase of Development | Phases of Work in TIP | Prior Obligations | TIP Database Links | Total Amount Programmed in FYs 2020-23 TIP | Federal Amount Programmed in FYs 2020-23 TIP | FYs 2020-23 TIP Obligated | Remaining Obligations | Remaining Local Match | Percent of Total Cost in TIP | Federal Share of Programmed Funds | Percent of TIP Amount Obligated | Policy #8 (Match Past Due) | Policy #10 (Obligation Past Due) | Phases of Work2 | PE-N | PE-D | ROW | CONST | Funding Type | Inactivity | Years Programmed2 | Obligation Past Due | Assurance of Match | Analyze | Program Type | TIP START | NTP NEPA | NEPA Approved | NTP Design | NTP ROW | NTP CONST | COMPLETE | Pre NEPA | NEPA | Design | ROW3 | Construction | Total Years
Gallatin | East-West Corridor (Albert Gallatin Avenue (SR-174) / Hatten Track Road Extension) | Sumner | 2 | 13 | 13.4575 | N/A | New Road | 2008-51-032 | 111041 | 111041.00 | 2008 | 40000000 | 2021 | Construction | CONSTRUCTION | 28045790 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=480 | 4200000 | 3360000 | 0 | 3360000 | 840000 | 10.5% | 8.4% | 0% | Yes | Yes | 2 |  |  |  | Y | U-STBG, HIP |  | 1 | 1 |  | Yes |  | 2008-06-01 | 2009-04-27 | 2016-06-21 | 2011-09-13 | 2013-05-23 | 2018-09-10 | 2021-11-12 | 0.90411 | 2.3808 | 1.6932 | 5.3041 | 3.1753 | 13.4575
Gallatin | Gallatin Citywide Sidewalk Improvements - Phase 1 | Sumner | 2 | 6 | 5.7836 | N/A | Sidewalks | 2015-56-067 | 123482 | 123482.00 | 2015 | 700000 | 2020 | Complete | CONSTRUCTION | 406296 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=851 | 240162.3 | 192130 | 0 | 192130 | 48032.5 | 34.31% | 27.45% | 0% | No | No | 2 |  |  |  | Y | U-TAP |  | 1 | 1 |  | Yes | ATP | 2015-06-01 | 2016-09-08 | 2017-06-27 | 2017-07-11 | 2019-07-02 | 2019-07-02 | 2021-03-12 | 1.274 | 0.83836 | 1.9753 | 0 | 1.6959 | 5.7836
Gallatin | Gallatin ITS & Signal Coordination Project | Sumner | 2 | 6 | 6.4548 | N/A | ITS | 2015-57-216 | 123413 | 123413.00 | 2015 | 1886500 | 2020 | Construction | CONSTRUCTION | 103000 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=873 | 1608500 | 1608500 | 1495731 | 112769 | 0 | 85.26% | 85.26% | 92.99% | N/A | Yes | 2 |  |  |  | Y | CMAQ |  | 1 | 1 | N/A | Yes |  | 2015-06-01 | 2016-10-14 | 2017-05-11 | 2017-06-08 | 2018-02-21 | 2021-09-01 | 2021-11-12 | 1.3726 | 0.64932 | 0.70685 | 3.5288 | 0.19726 | 6.4548
Gallatin | Nashville Pike Sidewalk | Sumner | 1 | 4 | 4.4521 | 1.6521 | Sidewalks | 2017-56-020 | 125506 | 0018389 | 2017 | 979054 | 2020 | Design | PE-D, CONSTRUCTION | 36000 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=925 | 934054 | 747243 | 36042 | 711201 | 178710.75 | 95.4% | 76.32% | 4.823% | Yes | Yes | 3 |  | Y |  | Y | CMAQ |  |  | 1 |  | Yes |  | 2017-06-01 | 2018-06-20 | 2020-01-09 | 2020-03-19 | 2021-11-12 |  |  | 1.0521 | 1.7479 | 1.6521 | N/A | N/A | 4.4521
Gallatin | Rucker Stewart Middle SRTS | Sumner | 1 | 5 | 5.4521 | N/A | Multi-Modal Upgrades | 2016-56-236 | 123748 | 123748.00 | 2016 | 477606 | 2020 | Construction | CONSTRUCTION | 25000 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=920 | 477606 | 431996 | 386203 | 45793 | 0 | 100% | 90.45% | 89.4% | N/A | No | 2 |  |  |  | Y | TAP |  | 1 |  | N/A | Yes |  | 2016-06-01 | 2017-10-30 |  | 2017-01-12 | 2020-07-21 | 2020-07-21 | 2021-11-12 | 1.4137 | -0.79726 | 3.5233 | 0 | 1.3123 | 5.4521
Gallatin | Gallatin ITS Phase 2 | Sumner | 0 |  | 0.44932 | 0.19178 | ITS | 2021-57-118 | 131553 |  |  | 1565640 | 2023 | NEPA | PE, CONSTRUCTION | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1100 | 1565640 | 1565640 | 20000 | 1545640 | 0 | 100% | 100% | 1.277% | No | No | 3 | Y | Y |  | Y | CMAQ |  |  |  |  | Yes |  | 2015-06-01: 2021-06-01; 2016-10-14: 2021-09-03; 2017-06-08: 2021-11-12 | 0.25753 | 0.19178 | N/A | N/A | N/A | 0.44932
Gallatin | Lock 4 Multiuse Trail | Sumner | 0 |  | 0.44932 | 0.17534 | Greenway | 2021-56-119 | 131660 |  |  | 4800770 | 2023 | NEPA | PE, ROW, CONSTRUCTION | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1101 | 4800770 | 3582920 | 80000 | 3502920 | 1137850 | 100% | 74.63% | 2.233% | No | No | 3 |  | Y | Y | Y | CMAQ |  |  |  |  | Yes |  | 2015-06-01: 2021-06-01; 2016-10-14: 2021-09-09; 2017-06-08: 2021-11-12 | 0.27397 | 0.17534 | N/A | N/A | N/A | 0.44932
Gallatin | Vol State-Gap Trail - Phase 1 | Sumner | 0 |  | 0.1863 | 0.021918 | Greenway | 2021-56-124 | 132027 |  |  | 999016 | 2022 | NEPA | PE, ROW, CONSTRUCTION | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1105 | 999016 | 0 | 0 | 0 | 49951 | 100% | 0% | N/A | No | No | 3 | Y |  | Y | Y | STATE |  |  |  | N/A | Maybe |  | 2015-06-01: 2021-09-05; 2016-10-14: 2021-11-04; 2017-06-08: 2021-11-12 | 0.16438 | 0.021918 | N/A | N/A | N/A | 0.1863
Local Projects
Project Name | TIP ID# | Improvement | Location | Lead Agency | Total Cost
East-West Corridor (Albert Gallatin Avenue (SR-174) / Hatten Track Road Extension) | 2008-51-032 | New Road | Sumner County | Gallatin | 40000000
Gallatin Citywide Sidewalk Improvements - Phase 1 | 2015-56-067 | Sidewalks | Sumner County | Gallatin | 700000
Gallatin ITS & Signal Coordination Project | 2015-57-216 | ITS | Sumner County | Gallatin | 1886500
Rucker Stewart Middle SRTS | 2016-56-236 | Multi-Modal Upgrades | Sumner County | Gallatin | 477606
Nashville Pike Sidewalk | 2017-56-020 | Sidewalks | Sumner County | Gallatin | 979054
Gallatin ITS Phase 2 | 2021-57-118 | ITS | Sumner County | Gallatin | 1565640
Lock 4 Multiuse Trail | 2021-56-119 | Greenway | Sumner County | Gallatin | 4800770
Vol State-Gap Trail - Phase 1 | 2021-56-124 | Greenway | Sumner County | Gallatin | 999016
Widening of Vietnam Veterans Boulevard (SR-386) and Long Hollow Pike (SR-174) and Offit Drive Connector | 2023-52-166 | Road Widening | Sumner County | TDOT | 111820000
TIP Amendment
Tip Amendment # | TIP ID # | RTP ID | Project | Requested By | Proposed Changes | Total Project Cost | Amendment Description
2023-004 | 2023-52-166 | 2609; 2611 | Widening of Vietnam Veterans Boulevard (SR-386) and Long Hollow Pike (SR-174) and Offit Drive Connector | TDOT | Add Project | 111820000 | This project Involves the widening of Vietnam Veterans Boulevard (SR-386) from near St. Blaise Road lo Long Hollow Pike (SR-174) from 4 lo 6 lanes and the widening ofLong Hollow Pike (SR-17 4) from near Vietnam Veterans Boulevard (SR-386) to near Gwen Avenue from 4 lo 6 lenes. It also Includes the construction of a new connector road (Ofllt Drive) from the SR-174/SR-386 interchange to near Belvedere Drive.
2045_RTP_Projects_Submitted
Project Description |  |  |  | Programming Information |  |  | Priority
APP ID | PROJECT NAME | IMPROVEMENT TYPE | APPLICANT | COUNTY | RTP ID | TIP# | COST (2020) | DESIRED HORIZON | SOGR (20 MAX) | SFTY (30 MAX) | CONG (15 MAX) | ECON (15 MAX) | ENVT (10 MAX) | ALGN (10 MAX) | TOTAL (100 MAX) | RANK | TIER | LOCAL
2634 | Albert Gallatin Avenue (SR 174) - Hatten Track Road Extension | Roadway New | City of Gallatin | Su | 1052-120 | 2008-51-032 | 37.8077 | 2025 | 0 | 7 | 12 | 7 | 1 | 9 | 36 | 153 | **** | No
2622 | City of Gallatin ITS & Signal Coordination, Phase 1 | Roadway Traffic Operations | City of Gallatin | Su | No | 2015-57-216 | 1.8865 | 2025 | 0 | 12 | 9 | 3 | 1 | 7 | 32 | 201 | **** | No
2603 | Main Street/Nashville Pike (US 31E/SR 6) Safety and Streetscape Improvements | Roadway Safety | City of Gallatin | Su | 1259 -Funded | No | 5.37 | 2035 | 11 | 23 | 14 | 8 | 9 | 2 | 67 | 3 | *** | No
2600 | Red River Road/Long Hollow Pike (SR 25/SR 174) Widening | Roadway Widening | City of Gallatin | Su | 1652-180 | No | 10 | 2035 | 9 | 22 | 13 | 7 | 5 | 10 | 66 | 7 | *** | Yes
2633 | Blythe Avenue/Dorothy Jordan Ave. Widening | Roadway Widening | City of Gallatin | Su | No | No | 10.4 | 2035 | 6 | 22 | 12 | 8 | 10 | 2 | 60 | 10 | *** | No
2610 | South Water Avenue Reconstruction | Roadway Reconstruct | City of Gallatin | Su | 1238 -Funded | No | 2.285 | 2035 | 6 | 15 | 12 | 4 | 10 | 0 | 47 | 53 | *** | No
2607 | Maple Street Extension | Roadway New | City of Gallatin | Su | Illustrative (1216) | No | 16.75 | 2025 | 7 | 5 | 14 | 5 | 10 | 2 | 43 | 80 | *** | No
2621 | Smith Street Extension | Roadway New | City of Gallatin | Su | No | No | 11.25 | 2025 | 4 | 11 | 15 | 5 | 3 | 2 | 40 | 105 | *** | No
2617 | Red River Road (SR 25) Widening | Roadway Widening | City of Gallatin | Su | Illustrative (1256) | No | 4.1 | 2035 | 2 | 18 | 9 | 5 | 5 | 0 | 39 | 116 | ** | No
2618 | Long Hollow Pike (SR 174) Widening | Roadway Widening | City of Gallatin | Su | No | No | 6 | 2035 | 0 | 21 | 10 | 4 | 3 | 0 | 38 | 131 | ** | No
2613 | City of Gallatin ITS & Signal Coordination, Phase 2 | Roadway Traffic Operations | City of Gallatin | Su | No | No | 3 | 2025 | 4 | 13 | 12 | 4 | 1 | 2 | 36 | 153 | ** | No
2615 | Gallatin Traffic Operations Improvement Program | Roadway Traffic Operations | City of Gallatin | Su | 1237 -partially funded | No | 16 | 2035 | 0 | 23 | 9 | 3 | 1 | 0 | 36 | 153 | ** | No
2608 | Airport Road Widening | Roadway Widening | City of Gallatin | Su | 1243 -Funded | No | 75 | 2035 | 4 | 9 | 10 | 8 | 0 | 2 | 33 | 193 | ** | No
2641 | Gallatin Public Transit System | Transit Capital Expansion | City of Gallatin | Su | No | No | 0.771 | 2035 | 0 | 5 | 5 | 9 | 5 | 0 | 24 | 275 | * | No
2623 | Commerce Way Extension | Roadway New | City of Gallatin | Su | 2623 | No | 3.5 | 2035 | 0 | 0 | 6 | 8 | 7 | 0 | 21 | 292 | * | No
2628 | Sumner County Bicycle and Pedestrian Master Plan | Planning- Studies | City of Gallatin | Su | No | No | 0.1 | 2025 | 0 | 7 | 4 | 7 | 1 | 2 | 21 | 292 | * | No
2616 | Bison Trail Extension | Roadway New | City of Gallatin | Su | No | No | 4.5 | 2035 | 0 | 0 | 6 | 3 | 7 | 2 | 18 | 303 | * | No
2626 | Town Creek Greenway Extension | Multiuse Path- Greenway | City of Gallatin | Su | No | No | 13.5 | 2035 | 0 | 3 | 5 | 2 | 0 | 5 | 15 | 325 | * | No
2624 | Gallatin Volunteer State-GAP Greenway | Multiuse Path- Greenway | City of Gallatin | Su | No | No | 13 | 2035 | 0 | 1 | 6 | 2 | 0 | 2 | 11 | 335 | * | No
2612 | NET Corridor Sec 3 Extension | Roadway New | City of Gallatin | Su | Illustrative (1279) | No | 110.4 | 2045 | 0 | 0 | 6 | 3 | 1 | 0 | 10 | 336 | * | No
2045_RTP_Project_Ranking
ID | Applicant | County | Proposal | Project Name | Score | RANK | TIER | SOGR | SFTY | CONG | ECON | ENVT | ALGN | TIP ID | Est. $$ (Millions)
2600 | City of Gallatin | Su | Roadway Widening | Red River Road/Long Hollow Pike (SR 25/SR 174) Widening | *** | + | + | + | + | + | + | No | 10
2603 | City of Gallatin | Su | Roadway Safety | Main Street/Nashville Pike (US 31E/SR 6) Safety and Streetscape Improvements | *** | + | + | + | + | + | - | No | 5.37
2607 | City of Gallatin | Su | Roadway New | Maple Street Extension | *** | + | - | + | + | + | - | No | 16.75
2608 | City of Gallatin | Su | Roadway Widening | Airport Road Widening | ** | = | - | + | + | - | - | No | 75
2610 | City of Gallatin | Su | Roadway Reconstruct | South Water Avenue Reconstruction | *** | + | + | + | = | + | - | No | 2.29
2612 | City of Gallatin | Su | Roadway New | NET Corridor Sec 3 Extension | * | - | - | - | - | - | - | No | 110.4
2613 | City of Gallatin | Su | Roadway Traffic Operations | City of Gallatin ITS & Signal Coordination, Phase 2 | ** | = | + | + | = | - | - | No | 3
2615 | City of Gallatin | Su | Roadway Traffic Operations | Gallatin Traffic Operations Improvement Program | ** | - | + | + | - | - | - | No | 16
2616 | City of Gallatin | Su | Roadway New | Bison Trail Extension | * | - | - | - | - | + | - | No | 4.5
2617 | City of Gallatin | Su | Roadway Widening | Red River Road (SR 25) Widening | ** | - | + | + | + | + | - | No | 4.1
2618 | City of Gallatin | Su | Roadway Widening | Long Hollow Pike (SR 174) Widening | ** | - | + | + | = | - | - | No | 6
2621 | City of Gallatin | Su | Roadway New | Smith Street Extension | *** | = | + | + | + | - | - | No | 11.25
2622 | City of Gallatin | Su | Roadway Traffic Operations | City of Gallatin ITS & Signal Coordination, Phase 1 | **** | - | + | + | - | - | + | No | 1.89 | 2015-57-216
2623 | City of Gallatin | Su | Roadway New | Commerce Way Extension | * | - | - | - | + | + | - | No | 3.5
2624 | City of Gallatin | Su | Multiuse Path- Greenway | Gallatin Volunteer State-GAP Greenway | * | - | - | - | - | - | - | No | 13
2626 | City of Gallatin | Su | Multiuse Path- Greenway | Town Creek Greenway Extension | * | - | - | - | - | - | = | No | 13.5
2628 | City of Gallatin | Su | Planning- Studies | Sumner County Bicycle and Pedestrian Master Plan | * | - | - | - | + | - | - | No | 0.1
2633 | City of Gallatin | Su | Roadway Widening | Blythe Avenue/Dorothy Jordan Ave. Widening | *** | + | + | + | + | + | - | No | 10.4
2634 | City of Gallatin | Su | Roadway New | Albert Gallatin Avenue (SR 174) - Hatten Track Road Extension | **** | - | - | + | + | - | + | No | 37.81 | 2008-51-032
2641 | City of Gallatin | Su | Transit Capital Expansion | Gallatin Public Transit System | * | - | - | - | + | + | - | No | 0.77

## TDOT
COLOR KEY: | New Projects Submitted by Locals | Programmatic Investments | Top Regional Priorities | TDOT Projects in Current TIP | New Projects Submitted by TDOT | Local Projects in Current TIP | Attributes Taken from GNRC 2045 RTP Projects Application Story Map | Attributes from Recent Notes on Projects Table | Project Development Task Force Handout
Project Name | ID | TIP ID | APPLICANT | COUNTY | PROPOSAL-TYPE | COST ESTIMATE | SCORE | HORIZON | GRANT | 2025 | TIP URL | Termini | Length | Existing Lanes | Future Lanes | Status | Award | Improve Act | Amendments | Administrative Modificantions | Recent Notes on Projects | Lead Agency | Project Name2 | County3 | Analyze | Improvement Type | Program Type | MPO TIP # | TDOT PIN # | PINI # | Year Entered TIP | Years Programmed | Estimated Total Cost | Programmed Construction Year | Active/Current Phase of Development | Phases of Work in TIP | Prior Obligations | TIP Database Links | Total Amount Programmed in FYs 2020-23 TIP | Federal Amount Programmed in FYs 2020-23 TIP | FYs 2020-23 TIP Obligated | Remaining Obligations | Remaining Local Match | Percent of Total Cost in TIP | Federal Share of Programmed Funds | Percent of TIP Amount Obligated | Policy #8 (Match Past Due) | Policy #10 (Obligation Past Due) | Phases of Work2 | PE-N | PE-D | ROW | CONST | Funding Type | Development Duration | Inactivity Duration | Inactivity | Years Programmed4 | Obligation Past Due | Degrees of Concern | Assurance of Match | TIP START | NTP NEPA | NEPA Approved | NTP Design | NTP ROW | NTP CONST | COMPLETE | Pre NEPA | NEPA | Design | ROW5 | Construction | Total Years
Northeast Corridor (Vietnam Veterans-SR 386) Transit/Managed Lanes to SR 109 (Section 1, Section 2A) | 2861 | 2017-52-037 | GNRC/TDOT | Da,Su | Roadway Multi-modal | 369520000 | n/a | 2035 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2326/TipProjectInfo.aspx?tipprojectid=944 | I-65 to SR 6 | 6.5 | 4 | 8 | Funded | 511911264.7 | Yes |  |  | No | TDOT | Vietnam Veterans Parkway (SR-386) Transit Managed Lanes & Widening | Sumner | Yes | Road Widening |  | 2017-52-037 | 124720.00 |  | 2017 | 4 | 238000000 | N/A | Not Started | PE-N, PE-D | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=944 | 12000000 | 9600000 | 0 | 9600000 | N/A | 5.042% | 4.034% | 0% | N/A | N/A | 1 | Y | Y |  |  | NHPP | 4.4521 | 4.4521 | 1 |  |  | 1 | N/A | 2017-06-01 | 2021-11-12 | [5 empty] | 4.4521 | N/A | N/A | N/A | N/A | 4.4521
I-65 Weigh Station Improvements (near the Tennessee/Kentucky State Line) | 2840 | 2019-39-094 | TDOT | Ro | Other | 16295000 | 40 | 2025 | NHPP | 13036000 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1001 | n/a | n/a | 0 | 0 | Funded |  | Yes |  | This project has been modified to remove the last line of the project description: "The northbound I-65 site will be converted to truck parking." | Construction phase approved in 2024 of 2023-25 Three-Year Work Program | TDOT | I-65 Weigh Station Near the TN/KY State Line | Sumner | Yes | Road Upgrades |  | 2019-39-094 | 101558.00 |  | 2019 | 2 | 16500000 | N/A | ROW | ROW | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1001 | 3000000 | 2400000 | 1749494 | 650506 | N/A | 18.18% | 14.55% | 72.9% | N/A | N/A | 1 |  |  | Y |  | NHPP | 2.4521 | 1.2548 |  |  |  | 0 |  | 2019-06-01 | ? |  | 2000-12-18 | 2020-08-11 | 2021-11-12 |  | #VALUE! | #VALUE! | 19.6603 | 1.2548 | N/A | #VALUE!
I-65 Widening from Rivergate Pkwy to SR 41 | 2833 | 2018-12-054 | TDOT | Da,Su | Roadway Widening | 59000000 | 51 | 2035 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=964 | Rivergate Parkway to SR 41 | 12.7 | 4 | 6 | Funded |  | Yes | This project has been modified to correct the location county, update the length and termini, add $400,000 (federal) NHPP for PE-N in FY 2021 and shift $400,000 (federal) NHPP for PE-D to FY 2021. |  | Construction phase approved in 2025 of 2023-25 Three-Year Work Program <br /> | TDOT | I-65 Widening from Rivergate Parkway to near Blue Star Road (US31W) | Sumner | Yes | Road Widening |  | 2018-12-054 | 124263.01 |  | 2018 | 3 | 59000000 | N/A | Design | PE-D | 900000 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=964 | 1000000 | 800000 | 400000 | 400000 | N/A | 1.695% | 1.356% | 50% | N/A | N/A | 1 |  | Y |  |  | NHPP | 3.4521 | 0.19452 |  |  |  | 0 |  | 2018-06-01 | 2019-05-16 |  | 2021-09-02 | 2021-11-12 |  |  | 0.95616 | 2.3014 | 0.19452 | N/A | N/A | 3.4521
I-65 Widening from Bethel Rd (SR 257) to SR 25 | 2837 | 2019-32-092 | TDOT | Ro | Roadway Widening | 80000000 | 40 | 2035 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=999 | Bethel Rd (SR 257) to SR 25 | 18.4 | 4 | 6 | Funded | 110827292.6 | Yes |  | This project has been modified to correct the location county, update the length and termini, add $400,000 (federal) NHPP for PE-N in FY 2021 and shift $400,000 (federal) NHPP for PE-D to FY 2021. | No | TDOT | I-65 Widening from SR-257 to SR-25 | Robertson | Yes | Road Widening |  | 2019-32-092 | 124263.03 |  | 2019 | 2 | 79800000 | N/A | Design | PE-N, PE-D | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=999 | 1000000 | 800000 | 1200000 | -400000 | N/A | 1.253% | 1.003% | 150% | N/A | N/A | 1 | Y | Y |  |  | NHPP | 2.4521 | 0.16438 |  |  |  | 0 |  | 2019-06-01 | 2020-05-20 |  | 2021-09-13 | 2021-11-12 |  |  | 0.96986 | 1.3178 | 0.16438 | N/A | N/A | 2.4521
I-65 Widening from SR 25 to SR 109 | 2841 | 2019-32-093 | TDOT | Ro | Roadway Widening | 132500000 | 38 | 2035 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1000 | SR 25 to SR 109 | 15.6 | 4 | 6 | Funded | 183557703.4 | Yes | This project has been amended to add $68,500,000 state funds to the project. This project has been amended to add $19,200,000 federal NHPP funds to the project in FY 2022. | This project has been modified to add $123,200,000 federal NHPP funds in FY 2021.This project has been modified to add $4,120,000 (federal) NHPP funds in FY 2021.This project has been modified to remove "Exit 112" from the termini and to modify the project description. | No | TDOT | I-65 Widening from SR-25 to SR-109 | Robertson | Yes | Road Widening |  | 2019-32-093 | 124263.04 |  | 2019 | 2 | 184150000 | 2022 | Construction | PE-N, PE-D, CONSTRUCTION | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1000 | 184150000 | 147320000 | 127546569 | 19773431 | N/A | 100% | 80% | 86.58% | N/A | N/A | 3 | Y | Y |  | Y | NHPP | 2.4521 | N/A |  |  |  | 0 | N/A | 2019-06-01 | 2020-05-20 |  | 2020-12-21 | 2021-07-20 | 2021-07-20 | 2021-11-12 | 0.96986 | 0.58904 | 0.57808 | 0 | 0.31507 | 2.4521
SR 386 (Vietnam Veterans) at Forest Retreat Road Interchange | 2848 | No | TDOT | Su | Interchange New | 10276343 | 39 | 2035 | STBG-S | $ - |  | n/a to n/a | 0.6 | 0 | 0 | Funded |  | Yes |  |  | No | TDOT | Vietnam Veterans Parkway (SR-386) Transit Managed Lanes & Widening | Sumner | Yes | Road Widening |  | 2017-52-037 | 124720.00 |  | 2017 | 4 | 238000000 | N/A | Not Started | PE-N, PE-D | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=944 | 12000000 | 9600000 | 0 | 9600000 | N/A | 5.042% | 4.034% | 0% | N/A | N/A | 1 | Y | Y |  |  | NHPP | 4.4521 | 4.4521 | 1 |  |  | 1 | N/A | 2017-06-01 | 2021-11-12 | [5 empty] | 4.4521 | N/A | N/A | N/A | N/A | 4.4521
SR 109 Portland Bypass (South segment) | 2850 | 2011-51-108 | TDOT | Su | Roadway New | 34100000 | 19 | 2035 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=574 | SR 109 to SR 52 | 7.8 | 0 | 4 | Funded | 47240133.49 | Yes | This project has been amended to add $9,920,000 federal NHPP funds to the project. | This project has been modified to shift federal funds for ROW to state funding for the purpose of advance construction in FY 2022. | NTP for NEPA received for the Southern section. Confirm with TDOT. | TDOT | SR-109 Portland Bypass | Sumner | Yes | New Road |  | 2011-51-108 | 106634.01; 106634.02; 106634.03 |  | 2011 | 10 | 72100000 | N/A | ROW | ROW | 1280000 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=574 | 18600000 | 14880000 | 5276679 | 9603321 | N/A | 25.8% | 20.64% | 35.46% | N/A | N/A | 1 |  |  | Y |  | NHPP | 10.4575 | 0.14521 |  | 1 |  | 1 | N/A | 2011-06-01 | 2015-06-04 |  | 2017-11-01 | 2021-09-20 | 2021-11-12 |  | 4.011 | 2.4137 | 3.8877 | 0.14521 | N/A | 10.4575
SR 109 Portland Bypass (North segment) | 2849 | 2011-51-108 | TDOT | Su | Roadway New | 71530000 | 17 | 2035 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=574 | SR 52 to SR 109 | 4.2 | 0 | 4 | Funded | 99093453.04 | Yes | This amendment adds the project to the TIP with $800,000 federal NHPP funds in FY 2022. |  | Construction phase approved in 2025 of 2023-25 Three-Year Work Program (North Segment, from SR-52 to SR-109)<br /> | [7 empty] | 106634.01; 106634.02; 106634.03
Broadway (SR 6) Widening from East Broadway (SR 6) to Albert Gallatin Ave | 2851 | No | TDOT | Su | Roadway Widening | 4700000 | 31 | 2045 | STBG-S | $ - |  | East Broadway (SR 6) to Albert Gallatin Ave. | 2.6 | 3 | 4 | Funded | 9638023.66 | Yes |  |  | No | Hendersonville | Main Street (SR-6/US31E) Sidewalk Improvements | Sumner | Maybe | Sidewalks | MAG | 2021‐56‐122 | 132045 |  |  |  | 999200 | 2022 | Not Started | PE, ROW, CONSTRUCTION | 0 | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1103 | 999200 | 0 | 0 | 0 | 49960 | 100% | 0% | N/A | No | No | 3 | Y | Y | Y | Y | STATE | 0.44932 | 0.44932 |  |  |  | 0 |  | 2021-06-01 | 2021-11-12 | [5 empty] | 0.44932 | N/A | N/A | N/A | N/A | 0.44932
I-65 Widening from Bethel Rd (SR 257) to SR 41 | 2852 | 2022-52-133 | TDOT | Su,Ro | Roadway Widening | 84000000 | 40 | 2045 | NHPP | $ - | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1119 | SR 41 to SR 257 | 4.8 | 4 | 6 | Funded | 172254039.9 | Yes | This amendment adds the project to the TIP with $800,000 federal NHPP funds in FY 2022. |  | No | TDOT | I-65 Widening from SR-41/US-31W to Bethel Road (SR-257) | Davidson | No | Road Widening |  | 2022-52-133 | 124263.02 |  |  |  | 85000000 | N/A | NEPA | PE-D |  | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=1119 | 1000000 | 800000 | 0 | 800000 | N/A | 1.176% | 0.9412% | 0% | N/A | N/A | [6 empty] | 0 | 0 |  |  |  | 0
I-65 Widening from Rivergate Parkway to near Blue Star Road (US31W) | 2833 | 2018-12-054 | TDOT | Multi-County | Roadway Widening | 76000000 |  |  |  |  | http://tipapp.nashvillempo.org/MPO_TIPApp_2326/TipProjectInfo.aspx?tipprojectid=964 | [17 empty] | 124263.01
SR-109 Portland Bypass | 1051-222 | 2011-51-108 | TDOT | SU | New Road | 72100000 |  |  |  |  | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/TipProjectInfo.aspx?tipprojectid=574 | [17 empty] | 106634.01; 106634.02; 106634.03

## SC_TDOT_TIP_23-26
TDOT TIP 2024-2026
TIP Project ID # | Project Name | Type | Regional Plan ID | Lead Agency | TDOT PIN | County | Total Cost | Name/Route | Total Programmed | Location | Federal Share | Length | Air Quality Status | Federal Obligation* | Unobligated Balance | Phase
2018-12-055 | I-65 Widening from Rivergate Parkway to near Blue Star Road (US31W) | Road Widening | 2833 | TDOT | 124263.01 | Multi-County | 76000000 | I-65 | 75000000 | Rivergate Parkway to near Blue Star Road (US31W) | 60000000 | 3.10 miles | Exempt |  | 60000000 | Construction
2011-51-108 | SR-109 Portland Bypass | New Road | 1051-222 | TDOT | 106634.01; 106634.02; 106634.03 | Sumner County | 72100000 | SR-109 | 18600000 | Proposed SR-109 - Portland Bypass from SR-109 south of SR-76 to SR-109 near Kirby Dr | 4320000 | 7.65 miles | 6476679 | Non-Exempt | -2156679 | Construction
TDOT FY 24-26 Multimodal Program Final.pdf
TDOT TIP 2023-2025
TIP Project ID # | Project Name | Type | Regional Plan ID | Lead Agency | TDOT PIN | County | Total Cost | Name/Route | Total Programmed | Location | Federal Share | Length | Air Quality Status | Federal Obligation* | Unobligated Balance | Phase
2018-12-054 | I-65 Widening from Rivergate Parkway to near Blue Star Road (US31W) | Road Widening | 1612-153 | TDOT | 124263.01 | Multi-County | 59000000 | I-65 | 1000000 | Rivergate Parkway to near Blue Star Road (US31W) | 800000 | 3.10 miles | Exempt | 400000 | 400000 | Construction
2019-39-094 | I-65 Weigh Station Near the TN/KY State Line | Road Upgrades | 1639-124 | TDOT | 101558 | Robertson County | 16500000 | I-65 | 3000000 | Near the TN/KY State Line | 2400000 | 0.10 miles | Exempt | 1749494 | 650506 | Construction
2011-51-108 | SR-109 Portland Bypass | New Road | 1051-222 | TDOT | 106634.01; 106634.02; 106634.03 | Sumner County | 72100000 | SR-109 | 18600000 | Proposed SR-109 - Portland Bypass from SR-109 south of SR-76 to SR-109 near Kirby Dr | 4320000 | 7.65 miles | Non-Exempt | 6476679 | ($2,156,679.00) | Construction
TDOT FY 23-25 Multimodal Program Final.pdf

## PhasesOfWork
ID | Phase | Name | Description
1 | PLAN | 1-PLAN | Planning
2 | PE-N | 2-PE-N | Environmental Review
3 | PE-D | 3-PE-D | Final Design
4 | ROW | 4-ROW | Right-of-Way Acquisition
5 | UTIL | 5-UTIL | Utilities Relocation
6 | CONS | 6-CONS | Construction
7 | IMPL | 7-IMPL | Implementation
8 | MAIN | 8-MAIN | Maintenance

## Grants&FundingCodeDescriptions
Funding Source | Description | Source | Administration | Allocation | Program Details
ATCMTD | Advanced Transportation and Congestion Management Technologies Deployment | Federal | FHWA | Discretionary | Open
CMAQ | Congestion Mitigation and Air Quality Program | Federal | FHWA | Statewide | Open
ER | Emergency Relief Program | Federal | FHWA | Statewide | Open
FTA 5307 | Large Urban Transit Formula Funds for Nashville-Davidson Urbanized Area | Federal | FTA | Suballocated | Open
FTA 5307-M | Large Urban Transit Formula Funds for Murfreesboro Urbanized Area | Federal | FTA | Suballocated | Open
FTA 5310 | Enhanced Mobility for Seniors and Individuals with Disabilities | Federal | FTA | Statewide | Open
FTA 5337 | State of Good Repair Program | Federal | FTA | Statewide | Open
FTA 5339 | Bus and Bus Facilities Program for Nashville-Davidson Urbanized Area | Federal | FTA | Suballocated | Open
FTA 5339-M | Bus and Bus Facilities Program for Murfreesboro Urbanized Area | Federal | FTA | Suballocated | Open
HSIP | Highway Safety Improvement Program | Federal | FHWA | Statewide | Open
HSIP-R | Highway Safety Improvement Program - Railroad Improvements | Federal | FHWA | Statewide | Open
ILP | Interchange Lighting Program | State | TDOT | Statewide | Open
ITS | Intelligent Transportation Systems Program | Federal | FHWA | Statewide | Open
LIC | Local Interstate Connector Program | State | TDOT | Statewide | Open
LOCAL | Local revenue pledged in addition to any non-federal matching requirements to fund a phase of work | Local | Local
L-STBG | Urban Surface Transportation Block Grant - Small Urban Areas | Federal | FHWA | Suballocated | Open
M-CRP | Carbon Reduction Program for Murfreesboro Urbanized Area | Federal | FHWA | Suballocated | Open
M-CRRSAA | Highway Infrastructure Program-Coronavirus Response and Relief Supplemental Appropriations Act for Murfreesboro Urbanized Area | Federal | FHWA | Suballocated | Open
MMAG | Multimodal Access Grant | State | TDOT | Statewide | Open
M-STBG | Urban Surface Transportation Block Grant for Murfreesboro Urbanized Area | Federal | FHWA | Suballocated | Open
NHPP | National Highway Performance Program | Federal | FHWA | Statewide | Open
PHSIP | Highway Safety Improvement Program - Planning Set-aside | Federal | FHWA | Statewide | Open
PROTECT | Promoting Resilient Operations for Transformative, Efficient, and Cost-saving Transportation Program | Federal | FHWA | Suballocated | Open
SIA | State Industrial Access Program | State | TDOT | Statewide | Open
STATE | State revenue pledged in addition to any non-federal matching requirements to fund a phase of work | State | TDOT | Statewide
STBG | Surface Transportation Program - State Program | Federal | FHWA | Statewide | Open
TAP | Transportation Alternatives Program (State) | Federal | FHWA | Statewide | Open
U-CRP | Carbon Reduction Program for Nashville-Davidson Urbanized Area | Federal | FHWA | Suballocated | Open
U-CRRSAA | Highway Infrastructure Program-Coronavirus Response and Relief Supplemental Appropriations Act for Nashville-Davidson Urbanized Area | Federal | FHWA | Suballocated | Open
U-HIP | Highway Improvement Program - Nash-Davidson UZA | Federal | FHWA | Suballocated | Open
U-STBG | Urban Surface Transportation Block Grant for Nashville-Davidson Urbanized Area | Federal | FHWA | Suballocated | Open
U-TAP | Transportation Alternatives Program (MPO) | Federal | FHWA | Suballocated | Open
z.M-RSV | Reserve funding for Urban Surface Transportation Block Grant for Murfreesboro Urbanized Area | Federal | FHWA | Suballocated
z.U-RSV | Reserve funding for Urban Surface Transportation Block Grant for Nashville-Davidson Urbanized Area | Federal | FHWA | Suballocated

## Sponsor&Organizations
Organization Name | Organization Type | Primary Contact Name | Primary Contact Name: Title | Primary Contact Name: First | Primary Contact Name: Middle | Primary Contact Name: Last | Primary Contact Email | Primary Contact Phone | Associated TIP Projects
Belle Meade | Municipal Government | [7 empty] | 2022-16-162
Brentwood | Municipal Government | Lori Lange |  | Lori |  | Lange | lori.lange@brentwoodtn.gov | (615) 371-0080 | 2020-67-107
City of Berry Hill | Municipal Government | Joe Baker |  | Joe |  | Baker | jbaker@berryhilltn.net | (615) 292-5531 | 2015-17-217 2018-16-071
Columbia | Municipal Government | Glenn Harper |  | Glenn |  | Harper | gharper@columbiatn.com | (615) 560-1510 | 2021-28-112 2023-29-901
Eagleville | Municipal Government | Hellyn Riggins |  | Hellyn |  | Riggins | hriggins@eaglevilletn.com |  | 2020-311-097
Fairview | Municipal Government | Kevin Blackburn |  | Kevin |  | Blackburn | kblackburn@fairview-tn.org |  | 2023-69-902
Franklin | Municipal Government | Jonathan Marston |  | Jonathan |  | Marston | jonathan.marston@franklintn.gov | (615) 791-3218 | 2009-67-026 2011-62-011 2014-62-001 2017-66-045 2018-66-085 2018-67-063 2022-67-138
Franklin Transit Authority | Public Transit Agency | Stanton Higgs |  | Stanton |  | Higgs | shiggs@tmagroup.org |  | 2011-65-016 2015-65-060 2017-65-017 2018-65-056 2019-65-129 2019-65-130 2022-65-154
Gallatin | Municipal Government | Bill McCord |  | Bill |  | McCord | william.mccord@gallatin-tn.gov | (615) 452-5400 | 2008-51-032 2015-56-067 2015-57-216 2016-56-236 2017-56-020 2021-56-119 2021-56-124 2021-57-118 2022-54-150 2022-56-156 2022-56-160
GNRC | MPO | Anna Emerson |  | Anna |  | Emerson | amerson@gnrc.org |  | 2008-15-051 2014-85-015 2017-19-800 2022-89-145 2023-85-025 2023-85-147 2023-85-5555 2023-86-6666 2023-89-099 2023-89-7777
Goodlettsville | Municipal Government | Addam McCormick |  | Addam |  | McCormick | amccormick@goodlettsville.gov | (615) 851-2200 | 2011-110-141 2011-19-020 2018-56-084 2020-17-108 2022-17-149
Greenbrier | Municipal Government | [7 empty] | 2023-39-907
Hendersonville | Municipal Government | Sarah Lock |  | Sarah |  | Lock | slock@hvilletn.org | (615) 822-1016 | 2002-028 2002-029 2012-56-171 2017-52-014 2018-57-062 2021-56-122 2022-59-140 99-New-28 99-New-29
La Vergne | Municipal Government | Bo Logan |  | Bo |  | Logan | blogan@lavergnetn.gov | (615) 287-8702 | 2011-42-032 2020-47-105
Lebanon | Municipal Government | Paul Corder |  | Paul |  | Corder | paul.corder@lebanontn.org | (615) 444-3647 | 2017-77-025 2018-76-078 2021-77-113 2022-711-136 2022-76-158 2022-77-152 2023-79-903
Metro Nashville | County Government | Marty Sewell |  | Marty |  | Sewell | marty.sewell@nashville.gov |  | 2004-005 2008-14-030 2008-17-057 2011-16-092 2014-111-026 2014-111-027 2014-16-002 2014-16-003 2017-16-049 2017-19-026 2018-111-075 2018-16-070 2018-19-076 2019-14-086 2020-17-110 2020-19-109 2021-17-114 2021-19-125 2022-11-146 2022-16-142 2022-17-148
Millersville | Municipal Government | Andrew Pieri |  | Andrew |  | Pieri | buildinginspector@cityofmillersville.com |  | 2016-18-234 2017-56-046
Mt. Juliet | Municipal Government | Andy Barlow |  | Andy |  | Barlow | abarlow@mtjuliet-tn.gov | (615) 773-7957 | 2014-76-017 2016-76-237 2017-72-030 2017-76-041 2017-76-047 2018-76-068 2018-77-064 2020-76-100 2022-72-143 2022-72-144 2022-72-147 2022-76-135 2022-76-155 2022-77-153
Mt. Pleasant | Municipal Government | Kate Collier |  | Kate |  | Collier | kcollier@mtpleasant-tn.gov |  | 2018-26-082 2023-29-908
Murfreesboro | Municipal Government | Jim Kerr |  | Jim |  | Kerr | jkerr@murfreesborotn.gov | (615) 893-6441 | 2011-410-151 2011-410-152 2011-41-144 2011-42-143 2017-46-048 2017-47-019 2018-46-083 2021-44-115 2021-44-116 2021-47-128
Murfreesboro Transit | Public Transit Agency | Russ Brashear |  | Russ |  | Brashear | rbrashear@murfreesborotn.gov | (629) 201-6355 | 2005-006 2005-007 2008-45-089 2014-45-019 2014-45-020 2019-45-127 2023-45-029
Nashville MTA | Public Transit Agency | [7 empty] | 2008-15-048 2008-15-049 2008-15-052 2008-15-054 2011-15-133 2011-15-135 2011-15-137 2011-15-160 2014-15-005 2014-15-009 2015-111-069 2017-15-042 2022-111-134
Nolensville | Municipal Government | Derek Adams |  | Derek |  | Adams | dadams@nolensvilletn.gov | (615) 906-9530 | 2018-66-073
Oak Hill | Municipal Government | [7 empty] | 2018-16-069
Portland | Municipal Government | Carlton Cobb |  | Carlton |  | Cobb | ccobb@cityofportlandtn.gov |  | 2015-56-064 2018-56-079 2018-57-066 2020-56-104 2022-54-161 2023-59-904
Ridgetop | Municipal Government | Kelly Rider |  | Kelly |  | Rider | kelly.rider@ridgetoptn.org |  | 2016-37-233
RTA | Public Transit Agency | [7 empty] | 2008-85-091 2014-85-012 2014-85-023 2014-85-024 2017-85-044 2018-711-059 2018-85-053 2018-85-058 2019-85-126 2021-811-117
Smyrna | Municipal Government | Kevin Rigsby |  | Kevin |  | Rigsby | kevin.rigsby@townofsmyrna.org | (615) 491-3896 | 2011-42-061 2012-44-172 2012-47-173 2015-46-072 2017-47-029 2018-42-051 2018-44-065 2018-46-072 2018-46-080 2021-46-123 2022-411-137 2022-46-159
Springfield | Municipal Government | Kimberly Atlee |  | Kimberly |  | Atlee | kimberly.atlee@springfieldtn.gov |  | 2017-31-031 2023-39-905
Spring Hill | Municipal Government | Missy Stahl |  | Missy |  | Stahl | mstahl@springhilltn.org |  | 2018-26-074 2019-63-088 2022-67-151 2023-29-906
Sumner County | County Government | Josh Suddath |  | Josh |  | Suddath | jsuddath@sumnercountytn.gov |  | 2012-59-191 2014-54-052 2018-511-081 2022-511-141
TDOT | State Government | Jonathan Russell |  | Jonathan |  | Russell | jonathan.russell@tn.gov |  | 2011-51-108 2014-110-044 2014-111-051 2014-77-016 2014-82-049 2016-84-231 2017-12-012 2017-42-006 2017-52-037 2017-62-038 2017-87-040 2018-12-054 2018-62-055 2018-72-057 2019-12-100 2019-12-105 2019-12-106 2019-14-102 2019-17-091 2019-32-092 2019-32-093 2019-39-094 2019-42-095 2019-44-096 2019-44-110 2019-62-112 2019-62-115 2019-64-113 2019-72-087 2019-72-116 2019-73-090 2019-89-119 2020-14-101 2020-14-102 2020-14-103 2021-17-120 2021-17-121 2021-87-126 2021-87-127 2022-12-129 2022-52-133 2022-62-130 2022-62-131 2022-62-132 2023-12-011 2023-12-104 2023-14-107 2023-42-123 2023-44-005 2023-44-006 2023-44-007 2023-44-008 2023-44-009 2023-44-010 2023-72-001 2023-89-117 2023-89-118 2023-89-120 2023-89-122
Thompsons Station | Municipal Government | Micah Wood |  | Micah |  | Wood | mwood@thompsons-station.com |  | 2018-66-077 2020-66-098
Vanderbilt University | Non-Profit | [7 empty] | 2020-17-106
Walk Bike Nashville | Non-Profit | Meredith Montgomery |  | Meredith |  | Montgomery | meredith@walkbikenashville.org |  | 2020-19-111
White House | Municipal Government | Ceagus Clark |  | Ceagus |  | Clark | cclark@whitehousetn.gov |  | 2016-52-232 2022-511-139
Williamson County | County Government | Joe Horne |  | Joe |  | Horne | joe.horne@williamsoncounty-tn.gov |  | 2008-64-037 2022-66-163
Williamson County/TMA Group | Public Transit Agency | Stanton Higgs |  | Stanton |  | Higgs | shiggs@tmagroup.org |  | 2014-85-014 2015-65-075 2018-611-060 2019-65-128 2019-65-131 2022-65-157
Wilson County | County Government | Tom Brashear |  | Tom |  | Brashear | brasheart@wilsoncountytn.gov | (615) 449-2836

## Databases&Documentation
Name | Description | URL
GNRC Transportation Improvement Program for FYs 2020-2023 | A database of transportation projects in the Greater Nashville area for fiscal years 2020-2023, detailing project status, county, improvement type, and funding. | http://tipapp.nashvillempo.org/MPO_TIPApp_2023/#&&/wEXAQUKRmlsdGVyTGlzdAWpAlByb2plY3RTdGF0dXNTZWxlY3RlZD0wJkNvdW50eUZpbHRlckxpc3Q9MXxUcnVlLDN8VHJ1ZSw0fFRydWUsNXxUcnVlLDZ8VHJ1ZSw3fFRydWUsMjh8VHJ1ZSwyfFRydWUmSW1wcm92ZW1lbnRUeXBlRmlsdGVyTGlzdD02fFRydWUsNHxUcnVlLDl8VHJ1ZSw1fFRydWUsMXxUcnVlLDh8VHJ1ZSw3fFRydWUsMnxUcnVlLDN8VHJ1ZSZGdW5kaW5nRmlsdGVyTGlzdD0xOHxUcnVlLDExfFRydWUsMTN8VHJ1ZSwzfFRydWUsMjV8VHJ1ZSwyMHxUcnVlLDV8VHJ1ZSwxfFRydWUsMTd8VHJ1ZSwxMHxUcnVlLDE0fFRydWUsMjN8VHJ1ZUBNQ3IUJiZACPrHAa/58J9pkJpnzn5YrmZ9gQ5yGxM4
GNRC Transportation Improvement Program for FYs 2023-2026 | A database of transportation projects in the Greater Nashville area for fiscal years 2023-2026, providing information on project status, county, improvement type, and funding sources. | http://tipapp.nashvillempo.org/MPO_TIPApp_2326/#&&/wEXAQUKRmlsdGVyTGlzdAWpAlByb2plY3RTdGF0dXNTZWxlY3RlZD0wJkNvdW50eUZpbHRlckxpc3Q9MXxUcnVlLDN8VHJ1ZSw0fFRydWUsNXxUcnVlLDZ8VHJ1ZSw3fFRydWUsMjh8VHJ1ZSwyfFRydWUmSW1wcm92ZW1lbnRUeXBlRmlsdGVyTGlzdD02fFRydWUsNHxUcnVlLDl8VHJ1ZSw1fFRydWUsMXxUcnVlLDh8VHJ1ZSw3fFRydWUsMnxUcnVlLDN8VHJ1ZSZGdW5kaW5nRmlsdGVyTGlzdD0xOHxUcnVlLDExfFRydWUsMTN8VHJ1ZSwzfFRydWUsMjV8VHJ1ZSwyMHxUcnVlLDV8VHJ1ZSwxfFRydWUsMTd8VHJ1ZSwxMHxUcnVlLDE0fFRydWUsMjN8VHJ1ZVPzi9/4lH6CAuF2jSS/1xujVPBRAI0ZpHr66wQSl+DG
GNRC TIP Project Tracker | An online tool for tracking the progress of transportation projects included in the Greater Nashville Regional Council's Transportation Improvement Program. | https://gnrc.knack.com/tip-tracker
Greater Nashville Regional Council - 2045 RTP Projects Application | An interactive map application displaying transportation projects from the Greater Nashville Regional Council's 2045 Regional Transportation Plan. | https://gnrc.maps.arcgis.com/apps/MapSeries/index.html?appid=7fa45c7ed3944f39a499194d921b2552
TDOT iTRIP Dashboard | A visual dashboard displaying key information and statistics about Tennessee Department of Transportation's transportation projects, designed for easy interpretation and understanding. | https://www.arcgis.com/apps/dashboards/e14888bce2954050a10df5e949a1bc1d